## Cover Page
KIAMUTURI NURSERY CSR PROJECT MATERIAL AND LABOUR COSTS

## Costs - Updated
KIAMUTURI NURSERY CSR PROJECT MATERIAL AND LABOUR COSTS
MATERIAL COSTS
No. | Item Description | Date of Purchase | UoM | Quantity | Unit Cost (KShs) | Total Cost(KShs) | Status
1 | Special Sand | 30/7/2024 | Lorries (7 tonnes) | 2 | 16000 | 32000 | Paid
2 | Ordinary Ballast | 30/7/2024 | Lorries (7 tonnes) | 2 | 15000 | 30000 | Paid
3 | Stone (6 × 9") | 30/7/2024 | Feet | 300 | 65 | 19500 | Paid
4 | Cement | 31/7/2025 | Bags (50 kg) | 20 | 820 | 16400 | Paid
5 | Barbed Wire | 2024-01-08 | Rolls | 1 | 4500 | 4500 | Paid
6 | Chain Link (6 ft) | 2024-01-08 | Rolls | 3 | 3000 | 9000 | Paid
7 | Measuring Tape (Foot Kamba) | 2024-01-08 | Pcs | 1 | 700 | 700 | Paid
8 | U Nails | 2024-01-08 | Kg | 3 | 280 | 840 | Paid
9 | Hammer | 2024-01-08 | Pcs | 10 | 330 | 3300 | Paid
10 | Hand Saw | 2024-01-08 | Pcs | 5 | 350 | 1750 | Paid
11 | Ordinary Nails (3") | 2024-01-08 | Kg | 7 | 180 | 1260 | Paid
12 | Ordinary Nails (4") | 2024-01-08 | Kg | 5 | 180 | 900 | Paid
13 | Roofing Nails | 2024-01-08 | Kg | 4 | 280 | 1120 | Paid
14 | 2" Nails | 2024-01-08 | Kg | 4 | 180 | 720 | Paid
15 | Manilla Rope | 2024-01-08 | Pcs | 10 | 80 | 800 | Paid
16 | Sheet Metal Shears | 2024-01-08 | Pairs | 1 | 750 | 750 | Paid
17 | Ordinary Nails | 7/8/2024 to 15/8/2024 | Kgs | 3 | 190 | 570 | Paid
18 | Roofing Nails | 2024-09-08 | Kgs | 5 | 250 | 1250 | Paid
19 | Ordinary Nails | 2024-09-08 | Kgs | 4 | 200 | 800 | Paid
20 | Hand Gloves | 2024-09-08 | Pairs | 50 | 160 | 8000 | Paid
21 | Hand Gloves | 2024-09-08 | Pairs | 30 | 160 | 4800 | Paid
22 | Hand Gloves | 15/8/2024 | Pairs | 26 | 160 | 4160 | Paid
23 | Saddle Clamp (3 × 1 ½") | 15/8/2024 | Pcs | 1 | 1428.28 | 1428.28 | Paid
24 | GI Nipple (1 ½") | 15/8/2024 | Pcs | 2 | 140 | 280 | Paid
25 | Gate Valve (1½") | 15/8/2024 | Pcs | 1 | 2000 | 2000 | Paid
26 | GI Union (1½") | 15/8/2024 | Pcs | 2 | 300 | 600 | Paid
27 | HDPE Coupling (1½") | 15/8/2024 | Pcs | 8 | 1002.82 | 8022.56 | Paid
28 | HDPE Pipes (1½") | 15/8/2024 | Rolls | 10 | 12936.32 | 129363.2 | Paid
29 | Saddle Clamp (1½ × 1" ) | 15/8/2024 | Pcs | 1 | 422.24 | 422.24 | Paid
30 | GI Nipple - 1" | 15/8/2024 | Pcs | 2 | 60 | 120 | Paid
31 | Gate Valve (1") | 15/8/2024 | Pcs | 2 | 950 | 1900 | Paid
32 | GI Union (1") | 15/8/2024 | Pcs | 2 | 130 | 260 | Paid
33 | GI Elbow (1") | 15/8/2024 | Pcs | 3 | 60 | 180 | Paid
34 | GI Socket (1") | 15/8/2024 | Pcs | 1 | 60 | 60 | Paid
35 | GI Long Thread Nipple (1") | 15/8/2024 | Pcs | 1 | 65 | 65 | Paid
36 | Back Nut (1") | 15/8/2024 | Pcs | 2 | 50 | 100 | Paid
37 | Washer (1") | 15/8/2024 | Pcs | 2 | 0 | 0 | Paid
38 | Ball Valve (1") | 15/8/2024 | Pcs | 1 | 1300 | 1300 | Paid
39 | HDPE Pipe (1") | 15/8/2024 | LM | 50 | 49.4624 | 2473.12 | Paid
40 | GI Long Threaded Nipple (¾") | 15/8/2024 | Pcs | 1 | 40 | 40 | Paid
41 | Back Nut (¾") | 15/8/2024 | Pcs | 2 | 30 | 60 | Paid
42 | Washer (¾") | 15/8/2024 | Pcs | 2 | 0 | 0 | Paid
43 | Gate Valve (¾") | 15/8/2024 | Pcs | 2 | 700 | 1400 | Paid
44 | GI Nipple (¾") | 15/8/2024 | Pcs | 6 | 40 | 240 | Paid
45 | GI Union (¾") | 15/8/2024 | Pcs | 5 | 90 | 450 | Paid
46 | GI Tee (¾") | 15/8/2024 | Pcs | 3 | 70 | 210 | Paid
47 | GI Elbow (¾") | 15/8/2024 | Pcs | 6 | 60 | 360 | Paid
48 | Bib Tap (¾") | 15/8/2024 | Pcs | 3 | 600 | 1800 | Paid
49 | Stand (¾") - 3 ft | 15/8/2024 | Pcs | 7 | 330 | 2310 | Paid
50 | Socket (¾") | 15/8/2024 | Pcs | 7 | 17.4 | 121.8 | Paid
51 | PPR Pipe (¾") | 15/8/2024 | LM | 40 | 286.52 | 2865.2 | Paid
52 | GI Bush (¾ × ½") | 15/8/2024 | Pcs | 1 | 40 | 40 | Paid
53 | GI Nipple (½") | 15/8/2024 | Pcs | 2 | 30 | 60 | Paid
54 | GI Union (½") | 15/8/2024 | Pcs | 1 | 70 | 70 | Paid
55 | Gate Valve (½") | 15/8/2024 | Pcs | 1 | 500 | 500 | Paid
56 | Stand (½") - 3 ft | 15/8/2024 | Pcs | 1 | 230 | 230 | Paid
57 | GI Elbow (½") | 15/8/2024 | Pcs | 2 | 30 | 60 | Paid
58 | Bib Tap (½") | 15/8/2024 | Pcs | 1 | 450 | 450 | Paid
59 | PPR Pipe (½") | 15/8/2024 | pcs | 10 | 180.96 | 1809.6 | Paid
60 | Thread Tape | 15/8/2024 | Pcs | 6 | 29 | 174 | Paid
61 | Oxford Hinges - Quality | 15/8/2024 | Pairs | 8 | 200 | 1600 | Paid
62 | Hinges jua kali | 15/8/2024 | Pairs | 2 | 80 | 160 | Paid
63 | Neck tower bolt 4 inch | 15/8/2024 | Pcs | 7 | 120 | 840 | Paid
64 | Alm tower bolt | 15/8/2024 | Pcs | 7 | 120 | 840 | Paid
65 | Construction net 3 × 50m | 15/8/2024 | Rolls | 6 | 7800 | 46800 | Paid
66 | T Hinges 4 inches | 15/8/2024 | Pairs | 3 | 200 | 600 | Paid
67 | Galvanised wire 12G | 15/8/2024 | Rolls | 3 | 5500 | 16500 | Paid
68 | Binding wire 20KG | 15/8/2024 | Rolls | 1 | 3100 | 3100 | Paid
69 | Nylon Fundi rope | 15/8/2024 | Pcs | 10 | 80 | 800 | Paid | 233065
70 | Cement | 17/8/2024 | Bags | 4 | 850 | 3400 | Paid
71 | Silicon | 20/8/2024 | Tubes (250 ml) | 1 | 280 | 280 | Paid
72 | Cement | 20/8/2024 | Bags | 7 | 820 | 5740 | Paid
73 | Plumbing Fittings | 20/8/2024 | Assortment |  | 3400 | 3400 | Paid
74 | Ordinary Nails | 21/8/2024 | Kgs | 1 | 200 | 200 | Paid
75 | Ordinary Nails | 22/8/2024 | Kgs | 2 | 180 | 360 | Paid
76 | Red Oxide | 22/8/2024 | Kgs | 3 | 350 | 1050 | Paid
77 | Main Nursery Signage | 22/8/2024 | Pcs | 1 | 15580 | 15580 | Paid
78 | Bed Runners | 23/08/2024 | Pcs | 60 | 50 | 3000 | Paid
79 | Cement | 24/08/2024 | Bags | 5 | 850 | 4250 | Paid
80 | Bed Runners | 24/08/2024 | Pcs | 35 | 50 | 1750 | Paid
81 | Bed Runners | 26/08/2024 | Pcs | 13 | 50 | 650 | Paid
82 | Cement | 28/8/2024 | Assortment | 1 | 9450 | 9450 | 8600
83 | Plumbing Materials
84 | Sink
85 | Plumbing Materials | 28/8/2024 | Assortment | 1 | 880 | 880
86 | Plastic Seats | 2024-04-09 | Pcs | 2 | 2500 | 5000 | Paid
87 | GSSHG Signage | 2024-04-09 | Pcs | 1 | 3250 | 3250 | Paid
88 | Isuzu EA Foundation Sticker | 2024-04-09 | Pcs | 1 | 1750 | 1750 | Paid
89 | Murram | 2024-05-09 | Lorries | 2 | 12000 | 24000 | 14000
Subtotal for Material Costs: | [5 empty] | 460175
LABOUR COSTS
No. | Description | Timeline | UoM | Quantity | Unit Cost (KShs) | Total Cost(KShs) | Status
1 | Project Supervision | 4/8/2024 to 10/8/2024 | Man-days | 30 | 500 | 15000 | Unpaid
2 | Mason | 7/8/2024 to 22/8/2024 | Man-days | 9 | 1200 | 10800 | Paid
3 | Assistant Mason | 7/8/2024 to 22/8/2024 | Man-days | 2 | 700 | 1400 | Paid
4 | Carpenter | 7/8/2024 to 22/8/2024 | Man-days | 7 | 1200 | 8400 | Paid
5 | Assistant Carpenter | 7/8/2024 to 22/8/2024 | Man-days | 4 | 700 | 2800 | Paid
6 | Plumber | 7/8/2024 to 22/8/2024 | Man-days | 5 | 1200 | 6000 | Paid
7 | Project Supervision | 11/8/2024 to 17/8/2024 | Man-days | 30 | 500 | 15000 | Unpaid
8 | Project Supervision | 18/8/2024 to 24/8/2024 | Man-days | 30 | 500 | 15000 | Unpaid
9 | Casual Labourers (Fence Clearing) | 23/8/2024 | Man-days | 6 | 500 | 3000 | Paid
10 | (Casual Labourers) Filling of Seedling Bags | 23/8/2024 | Bags | 37400 | 2 | 74800 | Paid
11 | Soil Preparation | 23/8/2024 | Tasks | 1 | 3200 | 3200 | Paid
12 | Project Supervision | 25/8/2024 to 31/8/2024 | Man-days | 30 | 500 | 15000 | Unpaid
13 | Casual Labourers | 24/8/2024 | Man-days | 23 | 500 | 11500 | Paid
14 | Casual Labourers (Seed Bed Preparation) | 26/8/2024 | Beds | 7 | 1500 | 10500 | Paid
15 | Casual Labourers (Seed Bed Preparation) | 27/8/2024 | Beds | 7 | 1500 | 10500 | Paid
16 | Painter | 28/8/2024 to 3/9/2024 | Man-days | 6 | 1200 | 7200 | 3600
17 | Mason | 28/8/2024 | Man-days | 1 | 1200 | 1200 | 2400
18 | Assistant Mason | 28/8/2024 | Man-days | 1 | 700 | 700 | Unpaid
19 | Plumber | 28/8/2024 | Man-days | 2 | 1200 | 2400 | Unpaid
20 | Carpenter | 28/8/2024 | Man-days | 1 | 1200 | 1200 | Unpaid
21 | Assistant Carpenter | 28/8/2024 | Man-days | 1 | 700 | 700 | Unpaid
22 | Project Supervision | 1/9/2024 to 7/9/2024 | Man-days | 12 | 500 | 6000 | Unpaid
23 | Front Area Lanscaping Works | 2024-04-09 | Man-days | 5 | 500 | 2500 | Unpaid
24 | Plumber | 2024-04-09 | Man-days | 1 | 1200 | 1200 | Unpaid
25 | Murraming | 2024-05-09 | Man-days | 8 | 500 | 4000 | Unpaid
26 | Ceremony Preparations | 2024-05-09 | Man-days | 3 | 500 | 1500 | Unpaid |  | 231500
Subtotal for Labour Costs | [5 empty] | 231500
Paid Labour Costs | [5 empty] | 148900
Unpaid Labour Costs | [5 empty] | 82600
MISCELLANEOUS COSTS
No. | Description | Timeline | UoM | Quantity | Unit Cost (KShs) | Total Cost(KShs) | Status
1 | Transaction Fees | 7/8/2024 to 23/8/2024 |  |  |  | 2700 | Paid
2 | Transport | 2024-08-08 | Trips | 1 | 700 | 700 | Unpaid
3 | Transport | 20/8/2024 | Trips | 1 | 700 | 700 | Paid
4 | Transport | 24/8/2024 | Trips | 2 | 700 | 1400 | Paid
5 | Transport | 28/8/2024 | Trips | 1 | 500 | 500 | Unpaid
6 | Water Installation and Connection Fee | 2024-05-09 | Lot | 1 | 8000 | 8000 | Unpaid
Subtotal for Miscellaneous Costs | [5 empty] | 14000
REQUIRED ITEMS
No. | Description | Timeline | UoM | Quantity | Unit Cost (KShs) | Total Cost(KShs) | Status
1 | Seeds | 2024-05-09 | Kgs | 30 | 3500 | 105000 | Paid
2 | Planting Tubes (Seedling Bags) | TBD | Pcs | 20000 | 1.43 | 28600 | Unprocured
3 | Casual Labourers (Seedling Bags Filling) | TBD | Pcs | 20000 | 2 | 40000 | Unprocured
4 | Bed Runners | TBD | Pcs | 32 | 50 | 1600 | Unprocured
Subtotal for Miscellaneous Costs | [5 empty] | 175200
Total for Materials, Labour, Miscellaneous Costs and Labour | [5 empty] | 880875
Amount Paid | [5 empty] | 707145 |  | 60700 | 28600 | 89300
Amount Unpaid | [5 empty] | 173730
KEY
Paid Expense
Unpaid Expense
Unprocured
Partly Paid

## Dropdown
Options
Paid
Unpaid
Unprocured